## Sheet1
Master B’Nai Mitzvah Timeline (adapted from Timeline in Family Guidebook)
One year to Seven Months Prior
finalize hotel room block
email Rabbi for 1st meeting - Schedule meeting with Rabbi to review expectations and timeline
Select tutor, in consultation with Rabbi and Director of Education then contact tutor to discuss tutoring schedule
book photographer - for Friday and Saturday and Saturday night
Book DJ
Book location
Book music leader for service
Begin attending Shabbat and Bar/Bat Mitzvah services on regular basis
Begin researching and planning mitzvah project
Finalize guest list
Six Months Prior
Send out save the date by email to out of town invites
Begin working with b’nai mitzvah tutor on weekly basis
Read Torah and Haftarah in English for content
Continue attending Shabbat and Bar/Bat Mitzvah services on regular basis
Select song leader for Shabbat services
Select gabbai (person to call people to Torah) for Shabbat morning service
Begin working on mitzvah project
Finalize all financial obligations with Office Manager including balance of b'nai mitzvah fee
Start working on video, picture slideshow
Five to Six Months Prior
Start meeting w/ tutor 6 months before
Parents, grandparents begin to learn, review Torah blessings
Determine, review roles for siblings, other family members
Invite assign Torah readings, aliyot
Finalize guest list
Create invitation
Purchase tallit (prayer shawl) and kippot (head coverings)
Plan create table centerpieces, order candy
Finalize menu options for all catered meals
Review and pay deposits to vendors
Four to Five Months Prior
Schedule meeting with Music Lead and Rabbi for three months prior
Begin weekly meetings with Rabbi to review prayers, Torah, Haftarah
Begin Dvar Torah (teaching words of Torah) with Rabbi
Finalize service format with Rabbi
Three Months Prior
Meet with Music Lead and Rabbi to review Friday night service and Saturday Program
B'nai mitzvah start meeting weekly with Rabbi
Mail invitations, generally six to eight weeks prior to event
Purchase synagogue dress clothing for all family members as needed
Finalize parent speech during Saturday service
Finalize preparations for Kabbalat Shabbat (Friday evening) oneg
One-Two Months Prior
Submit introduction, photo, mitzvah project information to synagogue newsletter
Finalize details, lists, requirements, payments with all vendors
Plan food for weekend events
Review and finalize Dvar Torah
Complete plans for mitzvah project
Create program, song sheet page; review with Rabbi
Submit honors list to Rabbi
Confirm all facility arrangements with Office Manager
Complete Social Hall set up, tablecloth selection, etc. with Office Manager
Order, purchase flowers, plants for Sanctuary bimah
Delegate last minute errand support
Final Month
Review Torah readings, blessings with participants
Finalize preparations for rehearsals with participants
Create master list, finalize all payments with vendors
Breathe
Final 2 Weeks
Final practice session with Rabbi
Bring kippot, clips, programs, song sheets, plants, flowers, etc. to synagogue
Pick up key, candy baskets, tablecloths from Office Manager
Take family photos - scheduled?
The final practice session, usually held on the Friday afternoon immediately prior to the bar or bat mitzvah, is an important part of the preparation and supports your child and family in feeling confident. Please discuss the length, timing, and inclusion of family members with the Rabbi as you finalize your planning.